## Project Plan and Gantt
Project Name | Quan Li Dat Phong Karaoke
Project Manager | Hà Năng Thái
Start Date | 2016-08-23
End Date | 2016-10-10
s
Tasks | Responsible | Start | End | Days | Status
Lên Kế Hoạch | Hà Năng Thái | 2016-08-23 | 2016-08-28 | 5 | Complete
Thu Thập Yêu Cầu | Văn Phú Hoàng Vũ | 2016-08-24 | 2016-08-28 | 4 | Complete
Phân Tích Thiết Kế Hệ Thống | Hà Năng Thái | 2016-08-29 | 2016-09-05 | 7 | Complete
Thiết Kế Database | Lương Ngọc Huy Thanh | 2016-08-30 | 2016-09-03 | 4 | Complete
Code View | Văn Phú Hoàng Vũ | 2016-09-15 | 2016-10-15 | 30 | In Process
CodeModel | Lương Ngọc Huy Thanh | 2016-09-15 | 2016-10-15 | 30 | In Process
CodeColtroller | Hà Năng Thái | 2016-09-15 | 2016-10-15 | 30 | In Process
Demo | Hà Năng Thái | 2016-09-30 | 2016-10-04 | 4 | Complete
Fix Bug | Lương Ngọc Huy Thanh | 2016-10-04 | 2016-10-20 | 16 | Not started
Launch |  | 2016-08-23 | 2016-10-21 | 59

## Stakeholder List
Stakeholder List
Name | Position | Role in project | Email address | Requirements | Expectations
John Smith | VP of Product | Final approval of milestones | john@123.com | Downtime of no longer than 20 minutes | QA to take less than 1 week, marketing to promote new features in newsletter

## Cost Baseline
Cost Baseline
Item/task | % Complete | Base Cost | Cost | Actual Cost | % Budget Spent
Extra devices for QA testing | 50% | 2800 | 3500 | 3600 | 15%

## Communication Plan
Communication Plan
Communication Type | Deliverable | Description | Delivery Method | Frequency | Owner | Audience
Presentation | 15-minute Powerpoint presentation | Presentation to marketing team about new features | In-person | One time | Alex B. | Marketing team
Meetings | Standup meetings | Check in about status | In-person | 2x a week | John S. | Project team